## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-1 | Setup of project environment (JDK, Spring Boot, MySQL, IDE) | MUST HAVE | - | K Nithisha | 3- Completed
S1 | S1 | US-02 | Implement Task CRUD operations using Thymeleaf UI | MUST HAVE | US-01 | K Nithisha | 3- Completed
S1 | S1 | US-03 | Add filtering, sorting, and pagination in Task list UI | SHOULD HAVE | US-02 | K Nithisha | 3- Completed
S1 | S1 | US-04 | Add enums (Task Status, Priority) and UI improvements | SHOULD HAVE | US-02 | K Nithisha | 3- Completed
S2 | S2 | US-05 | Implement REST APIs for Task CRUD | MUST HAVE | US-02 | K Nithisha | 3- Completed
S2 | S2 | US-06 | Add REST API filtering, sorting, pagination | SHOULD HAVE | US-05 | K Nithisha | 3- Completed
S2 | S2 | US-07 | API testing using Postman | MUST HAVE | US-06 | K Nithisha | 3- Completed
S3 | S3 | US-08 | Integrate email service using SMTP | MUST HAVE | US-05 | K Nithisha | 3- Completed
S3 | S3 | US-09 | Perform unit testing using JUnit | COULD HAVE | US-08 | K Nithisha | 3- Completed
S3 | S3 | US-10 | Implement email OTP verification for users | COULD HAVE | US-08 | K Nithisha | 3- Completed
S4 | S4 | US-11 | Implement user authentication (Login & Registration) using Spring Security | MUST HAVE | US-10 | K Nithisha | 3- Completed
S4 | S4 | US-12 | Implement automatic email reminders for overdue and upcoming tasks | MUST HAVE | US-08 | K Nithisha | 3- Completed
S4 | S4 | US-13 | Develop dashboard to display task summary (Total, Completed, Pending, Overdue) | MUST HAVE | US-02 | K Nithisha | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Project setup (JDK, Spring Boot, MySQL, IDE) | 27/11/25 | 28/11/25 | K Nithisha | Build | 3- Completed | 5
US-02 | T-02 | Create Task entity and database table | 29/11/25 | 30/11/25 | K Nithisha | Coding | 3- Completed | 3
US-02 | T-03 | Implement Task CRUD operations | 2025-12-01 | 2025-12-03 | K Nithisha | Coding | 3- Completed | 3
US-03 | T-04 | Add filtering, sorting, pagination | 2025-12-04 | 2025-12-05 | K Nithisha | Coding | 3- Completed | 2
US-04 | T-05 | Add enums (Task Status, Priority) | 2025-12-06 | 2025-12-06 | K Nithisha | Coding | 3- Completed | 1
US-04 | T-06 | UI Improvements using Thymeleaf | 2025-12-08 | 2025-12-09 | K Nithisha | Coding | 3- Completed | 1
US-05 | T-07 | Design REST API structure and endpoints | 2025-11-12 | 2025-12-12 | K Nithisha | Coding | 3- Completed | 2
US-05 | T-08 | Implement Task CRUD REST APIs | 13/12/25 | 16/12/25 | K Nithisha | Coding | 3- Completed | 1
US-06 | T-09 | Add filtering, sorting, pagination in REST APIs | 17/12/25 | 19/12/25 | K Nithisha | Coding | 3- Completed | 2
US-07 | T-10 | API testing using Postman | 21/12/25 | 22/12/25 | K Nithisha | Testing | 3- Completed | 1
US-08 | T-11 | Configure SMTP email service | 26/12/25 | 27/12/25 | K Nithisha | Build | 3- Completed | 3
US-08 | T-12 | Integrate email service with application | 28/12/25 | 30/12/25 | K Nithisha | Coding | 3- Completed | 2
US-10 | T-13 | Implement email OTP generation | 2026-03-01 | 2026-01-04 | K Nithisha | Coding | 3- Completed | 2
US-10 | T-14 | OTP validation and user verification | 2026-05-01 | 2026-01-06 | K Nithisha | Coding | 3- Completed | 1
US-11 | T-15 | Implement user registartion using spring security | 2026-08-01 | 2026-01-10 | K Nithisha | Coding | 3- Completed | 1
US-11 | T-16 | Implement login and authentication | 2026-11-01 | 13/01/26 | K Nithisha | Coding | 3- Completed | 1
US-12 | T-17 | Implement Scheduled job for overdue task reminders | 15/01/26 | 17/01/26 | K Nithisha | Coding | 3- Completed | 1
US-12 | T-18 | Trigger email reminders for upcoming tasks | 18/01/26 | 19/01/26 | K Nithisha | Coding | 3- Completed | 2
US-13 | T-19 | Design dashboard UI for task summary | 19/01/26 | 21/01/26 | K Nithisha | Coding | 3- Completed | 1
US-13 | T-20 | Display task statistics (Completed, Pending, Overdue) | 21/01/26 | 22/01/26 | K Nithisha | Coding | 3- Completed | 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7